## Pre-Event
Topics | Subtopics | Checklist Items | Items Status | Deadline
Participants Curation | Creatives | Identify the list of creatives |  | 2022-01-01
Cold blast emails and calls
Sign up / Register them
Get more details regarding their presentation
| Thought Leaders | Identify the list of creatives |  | 2022-01-01
Cold blast emails and calls
Sign up / Register them
Register their Tickets
| Audience | Put out tickets for the event
Get details of the participant details and list
Marketing | Word of mouth marketing | Create the campaign
|  | Upload the campaign on various platforms |  | 1931-01-01
| Collaboration Marketting | Send an email to Arts unions for collaboration
Send an email to TFL for puttin up the posters
Send an email to Sponsors to onboard them
| Event platforms | Sell tickets to the event platforms
Marketing posters for the event platforms
Event Organisation | Place | Select the place for hosting the event |  | 2025-02-01
Plan the spatial organisation of the event
Confirm the dates of the events
Address the way finding issues inside and outside the event
| Food & Beverages | Arrange for sponsors to provide food & beverages
Understand all the allergy actions and list them
Arrange for vegetarian, vegan and non-vegetarian options
| Utilitities | Arrange for washroom and other necessary utilities
Understand the requirements from the presenters for audio and video
Procure audio visual utilities
Check the lighting and sound utilities
Arrange for placement like a step stool and other utilities
Arrange for tables for presenters to present their work

## Event Day
Topics | Checklist Items | Items Status
Participant Experience | Follow up with the participants a week before the event
Get the requirements from the participants for their presentation
Send reminder for the participants on the day of the event
Prepare the presentation for the event day to present the presenters
Understand the presenters details and their requirements to set up the event space
Prepare the list of thought leaders and present a small bit about them
Prepare a small presentation about the thought leaders
Welcome participants and thought leaders and introduce them to everyone
Prepare ice-breakers to start the networking opportunities
Collect any details required for the event from the participants
Marketing Experience | Post constant remindes on social media with the hashtags
Request participants to add stories and other forms of engagement media on their socials
Record and post behind the scenes of the event
Post small snippets of the events and add the QR code to the next event
Event Experience | Ensure that mic, projectors, lightings etc. work well before the event
Ensure the wayfinding systems are in place and understandable
Ensure that food and beverages are all stocked up
Ensure that the ushers and other volunteers arrive at the location at least an hour before the event
Ensure that the posters and other barnding materials are all put up
Ensure that the presentations and other materials are all in tact
Practice the flow of the event once to ensure that the flow is maintained
Follow are the organisers guidelines
Ensure that the participants have all arrived on time
Ensure that the participants are all briefed regarding the event guidelines before in hand

## Post-Event
Topics | Checklist Items | Items Status
Marketing | Ensure that all the media capture during the event has been posted on the socials
Ensure that buzz for the next event has been created
CRM | Ensure that all the media have been captured during the event have been shared with the attendees
Ensure a feedback regarding the event has been sent to the attendees 12 hours after the event
Send a link to join the community group on various social media to the attendees
Send a link to sign up to Forum By ReGo newsletters
Send a thank you note to the attendees and a small feedback
Ensure that all the CRM templates stick to the branding of Forum By ReGo